# PROJECT Brief – Expressions of Interest

| Programme | Lung Health Workstream, Beyond |
| --- | --- |
| Project | Co-ordination and Delivery of the Asthma Friendly Schools Programme |
| Programme Contact | Terri-Lynn Quigley, Programme Manager (Terri-Lynn.Quigley@alderhey.nhs.uk) Beyond CYP Transformation Programme (beyond@alderhey.nhs.uk) |
| Submissions | Expressions of interest including a comprehensive response and full cost profile to the requirements outlined in this brief should be submitted to the Beyond programme, (beyond@alderhey.nhs.uk) by 4pm on Wednesday 4th November 2026. Evidence of similar work undertaken, and any supporting information would be looked upon favourably. |

- Project Outline

Expressions of interest (EOI) are being sought from single organisations or partnerships from who are experienced in delivery and oversight of multi-site programmes of work to support the delivery and expansion of the Asthma Friendly Schools Programme across Cheshire and Merseyside.

The total amount of funding available to deliver co-ordination training and quality assurance is up to £30,000 (total) from agreement of contract to 31st March 2027.  It is anticipated that the training will be delivered through a combination of face to face and online methods.

- Project Background

NHS Cheshire and Merseyside children and young people’s (CYP) transformation programme: Beyond, was established during 2021/22.

The aim of the programme is to:

Give every Child and Young Person the best possible start in life, maximising opportunities to reach their potential: listen to their voices, respond to their needs, and transform their services, outcomes and life chances through integrated work across the Partnership.

The programme is aligned to the 10 Year Health Plan for England: fit for the future, taking a population health approach, with a “shift left” in delivery towards early intervention and prevention.

Asthma is a common long-term condition affecting children and young people and can have a significant impact on health, wellbeing, school attendance, participation in physical activity and educational attainment.

The Beyond Asthma Friendly Schools Programme has been established to support schools in developing consistent and effective arrangements for children and young people living with asthma.

The initiative provides a framework for schools, Public Health and primary and secondary healthcare services to work together to ensure that children and young people living with asthma receive safe and effective support across settings. The initiative is available to schools across Cheshire and Merseyside.

The accompanying Asthma Friendly Schools Policy and Standards sets out the requirements and expectations for schools participating in the initiative.

- The need

Cheshire and Merseyside (C&M) Integrated Care System (ICS) is committed to addressing health inequalities and improving outcomes for its population of over 2.7 million people, more than a quarter of whom are CYP. Many CYP across C&M experience significant social deprivation and poorer health outcomes, particularly those living in the most disadvantaged communities. A key priority across the region is "giving every child the best start in life", recognising that good health in childhood is fundamental to educational attainment, social development, emotional wellbeing and lifelong health outcomes.

Respiratory illness remains one of the leading causes of ill health in children and young people. Asthma is the most common long-term medical condition in childhood, affecting approximately one in eleven children and young people across the UK1. Despite being a manageable condition for most children, asthma continues to have a significant impact on health, education and quality of life. Poorly controlled asthma can result in breathlessness, sleep disturbance, reduced participation in physical activity, increased school absence, emergency healthcare utilisation and, in rare circumstances, preventable deaths.

Variation in outcomes across Cheshire and Merseyside reflects wider health inequalities. Children living in more deprived communities experience higher rates of asthma-related emergency department attendance and hospital admission, often linked to barriers in accessing care, environmental factors, housing conditions and lower levels of health literacy. School absence associated with asthma can adversely affect educational outcomes and wider life opportunities, further contributing to inequalities experienced throughout the life course.

Schools play a crucial role in supporting children and young people with asthma. Children spend a significant proportion of their time in educational settings, making schools an ideal environment to promote asthma awareness, support self-management, recognise deteriorating symptoms and ensure appropriate responses to asthma emergencies. However, knowledge and confidence in asthma management can vary considerably between settings and staff groups.

Reviews following high-profile asthma deaths have consistently highlighted the importance of improving awareness, communication, policy implementation and staff training within schools and community settings. Ensuring that staff understand asthma, recognise symptoms promptly and are confident in responding to emergencies is essential to keeping children safe and enabling them to participate fully in school life.

The purpose of this initiative is to increase awareness, engagement and participation in the Asthma Friendly Schools Programme and to increase the number of schools and community settings accessing approved asthma education and training. Through a consistent, evidence-based approach, the programme aims to improve asthma knowledge, strengthen organisational policies and procedures, support earlier intervention and ultimately reduce preventable asthma-related harm, helping every child and young person with asthma to thrive and achieve their full potential.

- Requirements

The Expression of Interest (EOI) is seeking organisations with experience of robust programme delivery and oversight of multi-site programmes of work, delivering health education and training, and supporting quality assurance processes to deliver the Asthma Friendly Schools Programme across Cheshire and Merseyside.

The programme aims to increase the number of schools taking part and help them achieve and maintain Asthma Friendly School accreditation. There are around 1,200 schools across Cheshire and Merseyside, with contact details currently available for 858 schools. So far, 15 schools have achieved accreditation and a further 329 are actively engaged in the programme, creating a significant opportunity to expand its reach.

Applicants should demonstrate how they will engage schools across Cheshire and Merseyside, using existing relationships and education networks. They should also explain how they will identify schools and areas where participation is currently lower and work with Local Authorities and other partners to encourage involvement.

Schools are encouraged to identify an Asthma Champion who will lead the programme within their school and act as a key contact. Providers should explain how they will support schools to identify and develop Asthma Champions. Innovative approaches are welcomed, but providers should ensure their delivery model is flexible enough to meet different local needs and levels of demand.

The successful provider will be responsible delivering a programme of work that engages schools, promotes the benefits of accreditation, supports registrations and training bookings, maintains communication with schools, and identifies barriers to participation. They will also provide regular feedback and intelligence to Beyond on emerging themes, challenges, opportunities, and gaps in engagement.

Clinical oversight of the Asthma Friendly Schools Programme will be provided by the Clinical Leadership team within Beyond.  The successful provider will deliver asthma training to school staff using approved materials supplied or authorised by Beyond. Training may be delivered in person or virtually. Responsibilities will include arranging training sessions, managing bookings and attendance, collecting feedback, maintaining records, and ensuring key staff groups, including PE staff, participate.

All trainers must complete training provided by Beyond’s clinical leads before delivering the programme. Providers must ensure only approved training materials are used and keep records showing all trainers have completed the required training.

Training will help schools understand and implement the Asthma Friendly Schools Standards and local asthma policies. Providers should promote training to a wide range of staff, including teachers, teaching assistants, senior leaders, pastoral staff, office staff, first aid staff, PE staff (including PE leads, PE teachers, assistants and coaches), Asthma Champions, and anyone who regularly works with children and young people within the school environment.

The programme aims for schools to be working towards Asthma Aware Accreditation with at least 80% of school staff to receive asthma education, including appropriate participation from PE staff. Where this is not achievable, particularly in larger schools, schools may work towards Asthma Aware Accreditation by training key staff groups.  Where possible, schools should become fully Asthma Aware Accredited.

Applicants must demonstrate strong relationships with schools, the ability to work across Cheshire and Merseyside, and the capacity to deliver training at scale. They should show how they will respond to varying levels of demand and engage schools in areas where participation is currently lower.

As part of the EOI, applicants should clearly describe their approach to school engagement, mobilisation, training delivery, and quality assurance. They should explain how they will support schools to achieve the Asthma Friendly Schools Standards, maximise participation, and provide data to demonstrate the programme’s reach, outcomes, and impact.

- Reporting and Governance

Oversight of the contract will be undertaken by the Lung Health workstream delivered by Beyond within the wider Beyond Governance arrangements.  Following the establishment of the project, the successful provider will be required to provide monthly updates and reports against an agreed set of key performance indicators including:

- Number of quality assurance contacts

- Type of school/education setting.

- Training attendance and completion.

- Participant feedback.

- Progress towards agreed targets.

- Barriers to participation.

- Actions undertaken to address barriers.

- Emerging risks and issues.

- Good practice and case studies where appropriate.

Schools contacted.

- Schools engaged.

- Schools expressing an interest.

- Schools registered/booking training.

- Training sessions delivered.

- Schools attending training.

- Number of staff trained.

- Number of PE staff trained.

- Geographical distribution of participating schools

# SECTION 2: APPLICATION FORM

| 1 | Please provide an overview of your experience of delivery and oversight of multi-site programmes of work were engaging with schools was key to success? (Max 500 words). |
| --- | --- |
| 2 | Please describe your proposed approach to delivering Asthma Friendly Schools training, support and quality assurance across Cheshire & Merseyside, including how you will help increase both the number of schools involved and coverage across the region (Max 700 words). Please include: - How training, support and quality assurance will be delivered. - How your approach will support growth and engagement across Cheshire & Merseyside. - The Key Performance Indicators (KPIs) you would use to measure success, including any suggested targets and why you feel these are appropriate. Please provide your costed model separately (Question 7). |
| 3 | Please explain where you have delivered this approach elsewhere and what were the outcomes? (Max 500 words). |
| 4 | Please describe your readiness to implement delivery across Cheshire & Merseyside (Max 500 words). |
| 5 | Please describe the governance arrangements within your organisation and detail how will you mitigate any organisational risks/ capacity issues that may arise down the line? Please consider the potential scale of delivery required when answering this question. (Max 400 words). |
| 6 | Please outline how outcomes will be captured, monitored and evaluated (Max 500 words). |
| 7 | Please provide a financial breakdown of your delivery model for the duration of the programme as described in question 2. |

# DECLARATION

| Name |  |
| --- | --- |
| Title |  |
| Organisation |  |
| Signature |  |
| Name |  |
| Title |  |
| Organisation |  |
| Signature |  |